## Sheet1
question | opt1 | opt2 | opt3 | opt4 | ans | desc
Select the option that suits the Manifesto for Agile Software Development | Individuals and interactions | Working software | Customer collaboration | All of the mentioned | Answer:d | Explanation: None.
Agile Software Development is based on | Incremental Development | Iterative Development | Linear Development | Both Incremental and Iterative Development | Answer:d | Explanation: The software is developed in increments with the customer specifying the requirements to be included in each increment and the highest priority is to satisfy the customer through early and continuous delivery of valuable software. They are iterative because they work on one iteration followed by improvements in next iteration
Which on of the following is not an agile method? | XP | 4GT | AUP | All of the mentioned | Answer:b | Explanation: The 4GT approach does not incorporate iteration and the continuous feedback,which is the fundamental aspect of an agile method.
Agility is defined as the ability of a project team to respond rapidly to a change. | True | False |  |  | Answer:b | Explanation: The aim of agile methods is to reduce overheads in the software process and to be able to respond quickly to changing requirements without excessive rework.
How is plan driven development different from agile development ? | Outputs are decided through a process of negotiation during the software development process | Specification, design, implementation and testing are interleaved | Iteration occurs within activities | All of the mentioned | Answer:c | Explanation: A plan-driven approach to software engineering is based around separate development stages with the outputs to be produced at each of these stages planned in advance.
6. How many phases are there in Scrum ? | Two | Three | Four | Scrum is an agile method which means it does not have phases | Answer:b | Explanation: There are three phases in Scrum.The initial phase is an outline planning phase followed by a series of sprint cycles and project closure phase.
Agile methods seem to work best when team members have a relatively high skill level. | True | False |  |  | Answer:a | Explanation: None.
Which of the following does not apply to agility to a software process? | Uses incremental product delivery strategy | Only essential work products are produced | Eliminate the use of project planning and testing | All of the mentioned | Answer:c | Explanation: Testing is a major part of each software development process which can’t be avoided.
Which three framework activities are present in Adaptive Software Development(ASD) ? | analysis, design, coding | requirements gathering, adaptive cycle planning, iterative development | speculation, collaboration, learning | all of the mentioned | Answer:c | Explanation: None.
In agile development it is more important to build software that meets the customers’ needs today than worry about features that might be needed in the future. | True | False |  |  | Answer:a | Explanation: None.
It is not possible to build software that meets the customers' needs today and exhibits | TRUE | B. False |  | Correct Answer : | FALSE
Which of the following traits need to exist among the members of an agile software | team? | A. Competence | B. Decision-making ability | C. Mutual trust and respect | D. All of the above | Correct Answer : | All of the above | Explanation : If members of the software team are to drive the characteristics of the process that is applied to build software, a number of key traits must exist among the people on an agile team and the team itself: 1. Competence: In an agile development (as well as software engineering) context, “competence” encompasses innate talent, specific software-related skills, and overall knowledge of the process that the team has chosen to apply. 2. Common focus: Although members of the agile team may perform different tasks and bring different skills to the project, all should be focused on one 3. Goal—to deliver a working software increment to the customer within the Time promised. 4. Collaboration: team members must collaborate—with one another and all other Stakeholders. 5. Decision-making ability: the team is given autonomy—decision-making authority for both technical and project issues. 6. Fuzzy problem-solving ability: Software managers must recognize that the agile team will continually have to deal with ambiguity and will continually be buffeted by change 7. Mutual trust and respect: 8. Self-organization: The team selects how much Work it believes it can perform within the iteration, and the team commits to The work
What are the three framework activities for the Adaptive Software Development | A. Analysis, design, coding | B. Feasibility study, functional model iteration, implementation | C. Requirements gathering, adaptive cycle planning, iterative development | D. Speculation, collaboration, learning | Speculation, collaboration, learning | Explanation : Adaptive Software Development (ASD) has been proposed by Jim Highsmith as a technique for building complex software and systems. The philosophical underpinnings of ASD focus on human collaboration and team selforganization. He defines an ASD “life cycle” that incorporates three phases, speculation, collaboration, and learning Speculation 1. Adaptive cycle planning 2. Mission statement 3. Project constraints 4. Basic requirements 5. Time-boxed release plan Collaboration 1. Requirements gathering 2. JAD 3. Mini-specs Learning 1. Components implemented/tested 2. Focus groups for feedback 3. Formal technical reviews 4. Postmortems
. Agility is nothing more than the ability of a project team to respond rapidly to | TRUE | FALSE |  |  | FALSE
Which of the following is not necessary to apply agility to a software process? | A. Eliminate the use of project planning and testing | B. Only essential work products are produced | C. Process allows team to streamline tasks | D. Uses incremental product delivery strategy | Correct Answer : | Eliminate the use of project planning and testing
In agile development it is more important to build software that meets the customers’ needs today than worry about features that might be needed in the future. | TRUE | FALSE |  |  | TRUE
What are the four framework activities found in the Extreme Programming (XP) process model? | A. analysis, design, coding, testing | B. planning, analysis, design, coding | C. planning, analysis, coding, testing | D. planning, design, coding, testing | planning, design, coding, testing
All agile process models conform to a greater or lesser degree to the principles stated in the “Manifesto for Agile Software Development”. | TRUE | FALSE |  |  | TRUE
Which is not one of the key questions that is answered by each team member at each daily Scrum meeting? | A. What did you do since the last meeting? | B. What obstacles are you creating? | C. What is the cause of the problem you are encountering? | D. What do you plan to accomplish be the next team meeting? | What obstacles are you creating?
The Dynamic Systems Development Method (DSDM) suggests a philosophy that is based on the Pareto principle (80% of the application can be delivered in 20% of the time required to build the complete application). | TRUE | FALSE |  |  | TRUE
Agile Modeling (AM) provides guidance to practitioner during which of these software tasks? | A. Analysis | B. Design | C. Coding | D. Testing | Both a and b
Agile Unified Process uses the classic UP phased activities (inception, elaboration, construction, transition) to help the team visualize the overall process flow | TRUE | FALSE |  |  | TRUE
Human aspects of software engineering are not relevant in today’s agile process models. | TRUE | FALSE |  |  | FALSE
Which of the following is not an important trait of an effective software engineer? | A. Attentive to detail | B. Brutally honest | C. Follows process rule dogmatically | D. Resilient under pressure | Follows process rule dogmatically
Group communication and collaboration are as important as the technical skills of an individual team member to the success of a team. | TRUE | FALSE |  |  | TRUE
Which of the following can contribute to team toxicity? | A. Frenzied work atmosphere | B. Inadequate budget | C. Poorly coordinated software process | D. Unclear definition of team roles | a, b, d
Agile teams are allowed to self-organize and make their own technical decisions. | TRUE | FALSE |  |  | TRUE
. Which of these factors complicate decision-making by global software teams | A. Complexity of problem | B. Different views of the problem | C. Law of unintended consequences | D. Risk associated with decision | All of the above.
Which three framework activities are present in Adaptive Software Development(ASD) ? | A analysis, design, coding | B requirements gathering, adaptive cycle planning, iterative development | C speculation, collaboration, learning | D all of the mentioned | C
Which phase include in DSDM (Dynamic systems development method) ? | a.Feasibility and business study | b.Functional model / prototype iteration | c.Design and build iteration Implementation | All | D
Scrum has ___ phases | Two | Three | Four | None
Test are automated in extreme programming | TRUE | FALSE |  |  | TRUE
In Scrum When Sprint Over? | After Completing all the sprint Backlog items | After Completing all the sprint Backlog tasks | After Completing the final testing | when the time box expires | D
What Is a Sprint Review? | Activity to Introspect and Adapt | Activity to improve Scrum Processes | Activity to seek approval for the work done | Activity to plan for the next Sprint | A