## Unit 3
Question | Opt1 | Opt2 | Opt3 | Opt4 | Answers | Description
Effective software project management focuses on | people, performance, payoff, product | people, product, performance, process | people, product, process, project | people, process, payoff, product | ANS:C
Effective software project management focuses on | determine the budget. | select a team organizational model. | determine the project constraints | establish the objectives and scope | ANS: D
4. Process framework activities are populated with | milestones | work products | QA points | all of the above | ANS: D
5. Constantine suggests four “organizational paradigms” for software engineering teams. The best project team organizational model to use when handling extremely complex problems is ________ . | Random paradigm | Open paradigm | Synchronous paradigm | Closed paradigm | ANS: A
6. Which of the following is the task of project indicators: | a) help in assessment of status of ongoing project | b) track potential risk | c) help in assessment of status of ongoing project & track potential risk | d) none of the mentioned | ANS:C
7. Which of the following does not affect the software quality and organizational performance? | a) Market | b) Product | c) Technology | d) People | ANS: A | Market is a collection of competitors, stakeholders, users each having different views on the product. So it does not affect the software quality.
8. The intent of project metrics is: | a) minimization of development schedule | b) for strategic purposes | c) assessing project quality on ongoing basis | d) minimization of development schedule and assessing project quality on ongoing basis | ANS: D | A project metric is a quantitative measure of the degree to which a system, component or process possesses an attribute.
9. Which of the following is not a direct measure of SE process? | a) Efficiency | b) Cost | c) Effort Applied | d) All of the mentioned | ANS: A | Efficiency is an indirect measure.
10. Which of the following is an indirect measure of product? | a) Quality | b) Complexity | c) Reliability | d) All of the Mentioned | ANS: D | All the mentioned options are indirect measures of a product.
11. In size oriented metrics, metrics are developed based on the ___________________ | a) number of Functions | b) number of user inputs | c) number of lines of code | d) amount of memory usage | ANS:C
12. Which of the following is not an information domain required for determining function point in FPA ? | a) Number of user Input | b) Number of user Inquiries | c) Number of external Interfaces | d) Number of errors | ANS: D | FPA includes five domains namely input, output, inquiries, interface and logical files.
13. Usability can be measured in terms of: | a) Intellectual skill to learn the system | b) Time required to become moderately efficient in system usage | c) Net increase in productivity | d) All of the mentioned | ANS: D
14. A graphical technique for finding if changes and variation in metrics data are meaningful is known as | a) DRE (Defect Removal Efficiency) | b) Function points analysis | c) Control Chart | d) All of the mentioned | ANS: C
15. Defects removal efficiency (DRE)depends on: | a) E – errors found before software delivery | b) D – defects found after delivery to user | c) Both E and D | d) Varies with project | ANS: C | DRE = E / (E + d).
16. Which of the following is not a metric for design model? | a) Interface design metrics | b) Component-level metrics | c) Architectural metrics | d) Complexity metrics | ANS: D | Complexity metrics measure the logical complexity of source code.
17. Statement and branch coverage metrics are part of | a) Analysis Model | b) Testing | c) Design Model | d) Source Code | ANS: B | These metrics lead to the design of test cases that provide program coverage.
18. Function Points in software engineering was first proposed by | a) Booch | b) Boehm | c) Albrecht | d) Jacobson | ANS: C | First proposed by Albrecht in 1979, hundreds of books and papers have been written on functions points since then.
19 . How many Information Domain Values are used for Function Point Computation? | a) three | b) four | c) five | d) six | ANS: C | The five values are: External Inputs, External Outputs, External Inquiries, Internal Logical Files and External Interface Files.
20. Function Point Computation is given by the formula | a) FP = [count total * 0.65] + 0.01 * sum(Fi) | b) FP = count total * [0.65 + 0.01 * sum(Fi)]. | c) FP = count total * [0.65 + 0.01] * sum(Fi) | d) FP = [count total * 0.65 + 0.01] * sum(Fi) | ANS: B | Option b is the correct formula for Function Point Computation.
21.Architectural Design Metrics are ___________ in nature. | a) Black Box | b) White Box | c) Gray Box | d) Green Box | ANS: A | They are “black box” in that they do not require any knowledge of the inner workings of a particular software component.
22. Structural complexity of a module i is given as S(i) = f*f (i). What does f symbolizes here? | a) “fan check-out” of module i | b) “fan check-in” of module i | c) “fan in” of module i | d) “fan out” of module i | ANS: D | Fan out is number of modules directly invoked by module i.
23. SMI stands for | a) Software Mature Indicator | b) Software Maturity Index | c) Software Mature Index | d) Software Maturity Indicator | ANS: B
24. As the SMI approaches 1.0, the software product starts becoming unstable | a) True | b) False | - | - | ANS: B | As the SMI approaches 1.0, the software product begins to stabilize.
25. SMI = [Mt – (Fa + Fc + Fd)]/Mt. Here Mt is the number of modules | a) in the current release | b) in the current release that have been changed | c) from the preceding release that were deleted in the current release | d) none of the mentioned | ANS: A
26. The amount of time that the software is available for use is known as | a) Reliability | b) Usability | c) Efficiency | d) Functionality | ANS: A
27. Usability in metric analysis is defined as the degree to which the software | a) stated needs | b) is easy to use | c) makes optimal use of system resources | d) none of the mentioned | ANS: B
28. Size and Complexity are a part of | a) Product Metrics | b) Process Metrics | c) Project Metrics | d) All of the mentioned | ANS: A | Product Metrics describe the characteristics of product.
29. Cost and schedule are a part of | a) Product Metrics | b) Process Metrics | c) Project Metrics | d) All of the mentioned | ANS: C | Project Metrics describe the project characteristics and execution.
30. Number of errors found per person hours expended is an example of a | a) measurement | b) measure | c) metric | d) all of the mentioned | ANS: C | Metric is a quantitative measure of the degree to which a system, component, or process possesses a given attribute.
31. Which of the following is not categorized under Product Operation of McCall’s Software Quality Factors? | a) Flexibility | b) Reliability | c) Usability | d) Integrity | ANS: A | Flexibility is a part of Product revision as per McCall’s Software Quality Factors.
32. The arc-to-node ratio is given as r = a/n. What does ‘a’ represent in the ratio? | a) maximum number of nodes at any level | b) longest path from the root to a leaf | c) number of modules | d) lines of control | ANS: D | ‘a’ represents the arcs or the lines of control.
33. Which of the following is not categorized under Component-Level Design Metrics? | a) Complexity Metrics | b) Cohesion Metrics | c) Morphology Metrics | d) Coupling Metrics | ANS: C | Morphology metrics are a part of High level design metrics.
34. Percentage of modules that were inspected is a part of | a) Product Metrics | b) Process Metrics | c) Project Metrics | d) All of the mentioned | ANS: B
35. Metric is the act of obtaining a measure. | a) True | b) False | - | - | ANS: B | Measurement is the act of obtaining a measure.
96. MTTC falls the the category of | a) correctness | b) integrity | c) maintainability | d) all of the mentioned | ANS: C | Mean time to change (MTTC) is the time it takes to analyze the change request, design an appropriate modification, implement the change, test it, and distribute the change to all users.
37. Identify the correct option with reference to Software Quality Metrics. | a) Integrity = [Sigma(1 – threat)] * (1 – security) | b) Integrity = [1 – Sigma(threat)] * (1 – security) | c) Integrity = [1 – threat * Sigma(1 – security)]. | d) Integrity = Sigma[1 – threat * (1 – security)]. | ANS: D
38. Constantine suggests four “organizational paradigms” for software engineering teams. The best project team organizational model to use when handling extremely complex problems is ________ . | Random paradigm | Open paradigm | Synchronous paradigm | Closed paradigm | ANS: B
39. You are working in TriumphTech as a project manager. What will you do to minimize the risk of software failure? | Request a large budget | You will increase the team size | Track progress | None of the above. | ANS: C
40. Which of the following is/are considered stakeholder in the software process? | Customers | End-users | Project managers | All of the above. | ANS: D
41. Which of these software characteristics are used to determine the scope of a software project? | Only performance. | Only context. | Information objectives, function, performance | None of the above. | ANS: C
42. Boehm suggests an approach that addresses project objectives, milestones and schedules, responsibilities, management and technical approaches and required resources, This principle is called as ______ . | W3HH principle | WHO principle | W5HH principle | None of the above. | ANS: A
43 . You are working in CareerRide as a project manager. Company wants to develop a project. You are also involved in planning team. What will be your first step in project planning? | Establish the objectives and scope of the product. | Determine the project constraints. | Select the team. | None of the above. | ANS: A
44. What are the signs that a software project is in trouble? | The product scope is poorly defined. | Deadlines are unrealisti | Changes are managed poorly. | All of the above. | ANS: D
45. Software quality assurance is an umbrella activity. | True | False | - | - | ANS: A
46. Effective software project management focuses on the four P’s. What are those four P’s? | People, performance, payment, product | People, product, process, project | People, product, performance, project | All of the above. | ANS: B
47. If P is risk probability, L is loss, then Risk Exposure (RE) is computed as_____ . | RE = P/L | RE = P + L | RE = P*L | RE = 2* P *L | ANS: C
48. If every requirement can be checked by a cost-effective process, then the SRS is _________ . | Verifiable | Traceable | Modifiable | Complete | ANS: A
49. A COCOMO model is ________ . | Common Cost Estimation Model. | Constructive Cost Estimation Model. | Complete Cost Estimation Model. | Comprehensive Cost Estimation Model | ANS: B
50. Which plan describes how the skills and experience of the project team members will be developed ? | HR Plan | Manager Plan | Team Plan | Staff Development Plan | ANS: D
51. Cost of Production = Right The First time cost (RTF +-----------) . | Cost of Deployment | Cost of Quality | Cost of maintenance | Cost of Production | ANS: C
52. Which Chart is a statistical technique to assess, monitor, and maintain the stability of a process? | Control Chart | Maintenance Chart | Bar Charts | None of these | ANS: A
53. Resource Histogram is an effective tool for staff planning and coordination. | True | False | - | - | ANS: A
54. Software scope is not a well-defined boundary, which encompasses all the activities that are done to develop and deliver the software product. | True | False | - | - | ANS: B
55. The software scope identifies what the product will do and what it will not do, what the end product will contain and what it will not contain. | True | False | - | - | ANS: A
56. Abbreviate the term PERT. | Program Evolution & Review Technique | Process Evolution & Review Tool | Project Evalution & Request Technique | None of the above | ANS: A
57. In project execution and monitoring, every project is divided into multiple phases according to that in which phase of SDLC all major tasks are performed? | Milestones checklist | Status reports | Activity monitoring | None of the above | ANS: A
58. Which chart is a tool that depicts project as network diagram that is capable of graphically representing main events of project in both parallel and consecutive way? | PERT chart | Gantt chart | Both A & B | None of the above | ANS: A
59. From the following methods which size of the software product can be calculated? | Counting the lines of delivered code | Counting delivered function points | Both A and B | None of the above | Both A & B
60. A software project manager is a person who undertakes the responsibility of carrying out the software project. | True | False | - | - | ANS: A
61. Software project manager is engaged with software management activities. He is responsible for ______ . | Project planning. | Monitoring the progress | Communication among stakeholders | All mentioned above | ANS: D
62. Which is the Estimation Software size should be known? | Time estimation | Effort estimation | Cost estimation | Software size estimation | ANS: C
63. Object inherits a class is known as _____ . | Maintenance | Operations | Transitional | Development | ANS: B
64.In Risk management process what makes a note of all possible risks, that may occur in the project? | Manage | Monitor | Categorize | Identification | ANS: D
65. In the Empirical Estimation Technique which model is developed by Barry W. Boehm? | Putnam model | COCOMO | Both A & B | None of the above | ANS: B
66. A Project can be characterized as _____ . | Every project may not have a unique and distinct goal. | Project is routine activity or day-to-day operations. | Project does not comes with a start time and end time. | e. None of the above. | ANS: D
67. Software project management is the process of managing all activities that are involved in software development, they are _____ . | Time | Cost | Quality management | All mentioned above | ANS: D
68. Which may be estimated either in terms of KLOC (Kilo Line of Code) or by calculating number of function points in the software? | Time estimation | Effort estimation | Cost estimation | Software size estimation | ANS: D
69. COCOMO stands for ______ . | COnsumed COst MOdel | COnstructive COst MOdel | COmmon COntrol MOdel | COmposition COst MOdel | ANS: B
70. Software project management comprises of a number of activities, which contains _________. | Project planning | Scope management | Project estimation | All mentioned above | ANS: D