## Sheet1
question | opt1 | opt2 | opt3 | opt4 | ans | description
1. Effective software project management focuses on | A. people, performance, payoff, product | B. people, product, performance, process | C. people, product, process, project | D. people, process, payoff, product | people, product, process, project
2. Organizations that achieve high levels of maturity in | A. True | B. False | - | - | TRUE
people management have a higher likelihood of
implementing effective software engineering processes
3.The first step in project planning is to | A. determine the budget. | B. select a team organizational model. | C. determine the project constraints | D. establish the objectives and scope | establish the objectives and scope
4. Process framework activities are populated with | A. milestones | B. work products | C. QA points | D. all of the above | all of the above
5. Project management is less important for modern | A. True | B. False | - | - | FALSE
software development since most projects are successful and
completed on time
6. Which of the following is not considered a stakeholder in | A. customers | B. end-users | C. project managers | D. sales people | end-users
the software process?
7. The best person to hire as a project team leader is the | A. True | B. False | - | - | FALSE
most competent software engineering practitioner available.

## Sheet2
Effective software project management focuses on
1. Effective software project management focuses on
2. Organizations that achieve high levels of maturity in |  |  | - | -
C. people, product, process, project
D. people, process, payoff, product
3.The first step in project planning is to |  |  |  | D. establish the objectives and scope | establish the objectives and scope
4. Process framework activities are populated with | A. milestones | B. work products | C. QA points | D. all of the above | all of the above
5. Project management is less important for modern | A. True | B. False | - | - | FALSE
software development since most projects are successful and
completed on time
6. Which of the following is not considered a stakeholder in | A. customers | B. end-users | C. project managers | D. sales people | end-users
the software process?
7. The best person to hire as a project team leader is the | A. True | B. False | - | - | FALSE
most competent software engineering practitioner available.
establish the objectives and scope
. Process framework activities are populated with
A. milestones
B. work products
C. QA points
D. all of the above
Correct Answer :
all of the above
. Project management is less important for modern
software development since most projects are successful and
completed on time
A. True
B. False
Correct Answer :
FALSE
. Which of the following is not considered a stakeholder in
the software process?
A. customers
B. end-users
C. project managers
D. sales people
. The best person to hire as a project team leader is the
most competent software engineering practitioner available
A. True
B. False
Correct Answer :
FALSE
. The best project team organizational model to use when
tackling extremely complex problems is the
A. closed paradigm
B. open paradigm
C. random paradigm
D. synchronous paradigm
Correct Answer :
open paradigm
. Which factors should be considered in choosing the
organizational structure for a software team?
A. degree of communication desired
B. predicted size of the resulting program
C. rigidity of the delivery date
D. size of the project budget
E. a, b, c
Correct Answer :
a, b, c
One of the best ways to avoid frustration during the
software development process is to
A. give team members more control over process and
technical decisions
B. give team members less control over process and
technical decisions.
C. hide bad news from the project team members until
things improve.
D. reward programmers based on their productivity.
Correct Answer :
give team members more control over process and
technical decisions
Small agile teams have no place in modern software
development.
A. True
B. False
Correct Answer :
FALSE
. Which of these software characteristics is not a factor
contributing to project coordination difficulties?
A. interoperability
B. performance
C. scale
D. uncertainty
Correct Answer :
performance
. Which of these software characteristics are used to
determine the scope of a software project?
A. context, lines of code, function
B. context, function, communication requirements
C. information objectives, function, performance
D. communications requirements, performance,
information objectives
Correct Answer :
information objectives, function, performance
. The major areas of problem decomposition during the
project scoping activity are the
A. customer workflow
B. functionality to be delivered
C. process used to deliver functionality
D. software process model
E. b and c
Correct Answer :
b and c
. Product and process decomposition occurs simultaneously
as the project plan evolves.
A. True
B. False
Correct Answer :
TRUE
When can selected common process framework activities
be omitted during process decomposition?
A. when the project is extremely small in size
B. any time the software is mission critical
C. rapid prototyping does not require their use
D. never the activities are invariant
Correct Answer :
never the activities are invariant
The W5HH principle contains which of the following
questions?
A. Why is the system being developed?
B. What will be done by whom?
C. Where are they organizationally located?
D. How much of each resource is required?
E. a, c d
Correct Answer :
a, c d